## Sheet1
Asset | Stage | Priority | Expected Time (Hrs) | Actual Time (Hrs) | Refrence | Expected Completion | Notes
Animation Concepts | Concept | 1 | 7 | 0 | https://trello.com/c/p0QilOvS | April 30th 2021 | Could not meet deadline pushed to end week of term 5
Load Ruiner Model | No Progress | 1 | 6 | 0 | https://trello.com/c/Ja8jlvUm | April 30th 2021 | Could not meet deadline pushed to end week of term 5
Menu Screen /Title Concept | Approval Recived - Refining Required | 1 | 4 | 4 | https://trello.com/c/TrFXH5Zy | April 30th 2021 | Given to Thomas
HUD Art | No Progress | 2 | - | - | https://trello.com/c/NjnT6L7T | May 30th 2021 | Recived update from evan and brandon for HUD elements (Buttons / Loading)
Dynamic Crosshair Concept | Concept/Refining | 2 | 2-8 hours | 2 | https://trello.com/c/mi5TZw3M | April 30th 2021 | Pushed to next term, no touching this according to the programmersw , its broken
Loading Screen Art | No Progress | 3 | 4 | 0 | https://trello.com/c/7VU5TLVk | April 30th 2022 | This is still unclear, pusheed to lowest prority
In Game Menu Art | No Progress | 2 | 4 | 0 | https://trello.com/c/GuBbBvAz | May 30th 2021 | Submitted some drafts for feedback
DONE
Machine UI/HUD | Concept/Refining | recived approval | 3 | 2 | https://trello.com/c/AREIWLvZ | DONE
Player HUD | Concept/Refining | recived approval | 2 | 5 | https://trello.com/c/22CfKLO7 | DONE
Sabotage/Item Concepts | Concept/Refining | recived approval | 1 | 2 | https://trello.com/c/nln7RmMe | DONE
| Concept/Refining | recived approval | 1 | 2 | https://trello.com/c/E4cbz50h | DONE
| Concept/Refining | recived approval | 1 | 2 | https://trello.com/c/wC1I7PZa | DONE
| Concept/Refining | recived approval | 1 | 2 | https://trello.com/c/FFPBqmdm | DONE
Character Reconcept | Refining | recived approval | 6 | 3 | https://trello.com/c/o4qTAiMn | DONE
priority list
|  | 1 | high
|  | 2 | Average
|  | 3 | low
|  | w | wishlist